## Project Schedule
Agreement Term: 5-11-2018 to 3-31-2023 Within this Scope of Work, "days" means working days. Changes to due dates must be approved in writing by the CAM, and may require approval by the Energy Commission's Executive Director or his/her designee.
Task/ Subtask # | Task/Subtask Name | Meeting Name | Product(s) | Due Date
1 | General Project Tasks
1.1 | Products
1.2 | Kick-off Meeting | Kick-off Meeting |  | 2018-05-11
|  |  | Updated Project Schedule (if applicable) | 7 days after determination of the need to update the documents
Updated List of Match Funds (if applicable)
Updated List of Permits (if applicable)
CAM Product
|  |  | Kick-off Meeting Agenda | 7 days prior to the kick-off meeting
1.3 | CPR Meeting | CPR Meeting #1 |  | 2019-10-30
|  | CPR Meeting #2 |  | 2021-03-25
|  |  | CPR Report | 15 days prior to the CPR meeting
Task Product(s)
CAM Products
|  |  | CPR Agenda | 5 days prior to the CPR meeting
List of Expected CPR Participants
|  |  | Schedule for Providing a Progress Determination | 15 days after CPR meeting
|  |  | Progress Determination | As indicated in the Schedule for Providing a Progress Determination
1.4 | Final Meeting | Final Meeting |  | 2022-11-30
|  |  | Final Meeting Agreement Summary (if applicable) | 7 days after the final meeting
Schedule for Completing Agreement Closeout Activities
All Draft and Final Written Products
1.5 | Progress Reports and Invoices |  | Progress Reports | 10 days after the first of each month
|  |  | Invoices | 10 days after the first of each month or quarter
1.6 | Final Report
1.6.1 | Final Report Outline |  | Draft Final Report Outline | 2022-05-31
|  |  | Final Report Outline | As determined by the CAM
CAM Product
|  |  | Style Manual | At least 2 months prior to the final report outline due date
|  |  | Comments on Draft Final Report Outline | 10 days after receipt of the Draft Final Report Outline
|  |  | Approval of Final Report Outline | 10 days after receipt of the Final Report Outline
1.6.2 | Final Report |  | Draft Final Report | 2022-07-29
|  |  | Final Report | 2022-09-30
CAM Products
|  |  | Comments on Draft Final Report Outline | 30 days after receipt of the Draft Final Report
1.7 | Match Funds |  | Match Funds Status Letter | 2 days prior to the kick-off meeting
|  |  | Supplemental Match Funds Notification Letter (if applicable) | 10 days after receipt of additional match funds
|  |  | Match Funds Reduction Notification Letter (if applicable) | 10 days after any reduction of match funds
1.8 | Permits |  | Permit Status Letter | 2 days prior to the kick-off meeting
|  |  | Updated List of Permits (if applicable) | 10 days after determination of the need for a new permit
Updated Schedule for Acquiring Permits (if applicable)
|  |  | Copy of Each Approved Permit (if applicable) | 7 days after receipt of each permit
1.9 | Subcontracts |  | Draft Subcontracts (if required by the CAM) | As determined by the CAM
Final Subcontracts
1.1 | Technical Advisory Committee (TAC) |  | List of Potential TAC Members | 2 days prior to the kick-off meeting
|  |  | List of TAC Members | 7 days after finalization of the TAC
|  |  | Documentation of TAC Member Commitment | 7 days after receipt of the documentation
1.11 | TAC Meetings | TAC Meeting #1 |  | 2018-09-12
|  | TAC Meeting #2 |  | 2019-09-11
|  | TAC Meeting #3 |  | 2020-09-09
|  | TAC Meeting #4 |  | 2021-09-15
|  | TAC Meeting #5 |  | 2022-09-07
|  |  | Draft TAC Meeting Schedule | 20 days after the kickoff meeting
|  |  | Final TAC Meeting Schedule | 10 days after the first TAC meeting
|  |  | Draft TAC Meeting Agendas | 20 days prior to each TAC meeting
TAC Meeting Back-up Materials
|  |  | Final TAC Meeting Agenda | 7 days prior to each TAC meeting
|  |  | TAC Meeting Summaries | 10 days after each TAC meeting
Technical Tasks
2 | Requirement Analysis |  | Data Exchange Requirements and Assessment Presentation | 2019-03-15
|  |  | Data Exchange Implementation and Validation Plan Presentation | 2019-06-20
3 | Implementation |  | CPR Report #1 | 2019-10-30
4 | Testing and Validation |  | Testing and Validation Presentation | 2021-08-16
5 | Finalize Production |  | Draft Developer & User Training Documentation | 2021-10-25
|  |  | CPR Report #2 | 2021-03-25 | Change to 9/30/21, per discussion 4/15/21
|  |  | Final Developer & User Training Documention | 2021-11-25
|  |  | Final Product Release Report | 2021-12-01
6 | Evaluation of Project Benefits |  | Kick-off Meeting Benefits Questionnaire | 2018-06-08
|  |  | Mid-term Benefits Questionnaire | 2021-09-30
|  |  | Final Meeting Benefits Questionnaire | 2021-11-15
7 | Technology/Knowledge Transfer Activities |  | Updated Progress Power Point Slide | First Tuesday of each Month
|  |  | CAM Site Visit Schedule | 7 days prior to the kick-off meeting
|  |  | Draft Initial Fact Sheet | 2018-08-01
|  |  | Final Initial Fact Sheet | 2018-10-01
|  |  | Draft Final Project Fact Sheet | 2021-08-02
|  |  | Final Project Fact Sheet | 2021-10-01
|  |  | Draft Presentation Materials | 2018-12-28
|  |  | Final Presentation Materials | 2021-10-15
|  |  | Draft Technology/Knowledge Transfer Plan | 2019-03-15
|  |  | Final Technology/Knowledge Transfer Plan | 2019-06-18
|  |  | Draft Technology/Knowledge Transfer Report | 2021-06-15
|  |  | Final Technology/Knowledge Transfer Report | 2021-08-16
8 | Production Readiness Plan |  | Draft plan | 2021-08-16
|  |  | Final Plan | 2021-10-15